## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Project initialization and setup Spring Boot backend with MySQL database | MUST HAVE | Spring Boot Documentation | Yujesh shyam | 3- Completed
S1 | S1 | US-002 | Configure database connection and create Transaction entity and repository | MUST HAVE | mysql | Yujesh shyam | 3- Completed
S2 | S2 | US-003 | Implement transaction ingestion API to accept incoming transactions | MUST HAVE | rest api Documenation | Yujesh shyam | 3- Completed
S2 | S2 | US-004 | Develop rule-based fraud detection logic (RiskEngine) | MUST HAVE | fraud detection rules research | Yujesh shyam | 3- Completed
S3 | S3 | US-005 | Implement feature extraction module for transaction history analysis | SHOULD HAVE | java collections | Yujesh shyam | 3- Completed
S3 | S3 | US-006 | Integrate Machine Learning scoring service for fraud prediction | SHOULD HAVE | kaggle Dataset | Yujesh shyam | 3- Completed
S4 | S4 | US-007 | Combine rule-based and ML scoring to create hybrid risk scoring system | MUST HAVE | Risk Scoring logic | Yujesh shyam | 3- Completed
S4 | S5 | US-008 | Implement risk level classification (LOW, MEDIUM, HIGH) and action handling | SHOULD HAVE | business rules | Yujesh shyam | 3- Completed
S5 | S5 | US-009 | Store fraud evaluation results in FraudRisk database table | SHOULD HAVE | jpa repository | Yujesh shyam | 3- Completed
S5 | S6 | US-010 | Develop dashboard summary API to provide KPI statistics | SHOULD HAVE | springboot rest | Yujesh shyam | 3- Completed
s6 | s6 | US-011 | Implement fraud trend analytics API for time-based fraud visualization | MUST HAVE | Aggregation queries | Yujesh shyam | 3- Completed
s6 | s6 | US-012 | Implement risk distribution API (LOW / MEDIUM / HIGH counts) | MUST HAVE | sql group by | Yujesh shyam | 3- Completed
s6 | s6 | US-013 | Implement top risky merchants analytics API | SHOULD HAVE | pagination logic | Yujesh shyam | 3- Completed
s7 | s7 | US-014 | Develop recent transactions API for dashboard monitoring | SHOULD HAVE | query parameters | Yujesh shyam | 3- Completed
s7 | s7 | US-015 | Implement transaction search and filtering functionality | MUST HAVE | risk decision service | Yujesh shyam | 3- Completed
s7 | s7 | US-016 | Implement fraud alert system for high-risk transactions | MUST HAVE | spring security | Yujesh shyam | 3- Completed
s8 | s8 | US-017 | Develop authentication system with role-based access (Admin / Analyst) | MUST HAVE | spring boot actuator | Yujesh shyam | 3- Completed
s8 | s8 | US-018 | Implement system health monitoring API | MUST HAVE | react+tailwind | Yujesh shyam | 3- Completed
s9 | s9 | US-019 | Build React frontend dashboard with charts and KPI cards | SHOULD HAVE | dashboard apis | Yujesh shyam | 3- Completed
s9 | s9 | US-020 | Implement real-time transaction monitoring UI | MUST HAVE | alert apis | Yujesh shyam | 3- Completed
s10 | s10 | US-021 | Implement fraud notification handling and alert display | MUST HAVE | alert apis | Yujesh shyam | 3- Completed
s10 | s10 | US-022 | Perform system testing and deployment preparation | SHOULD HAVE | Docker | Yujesh shyam | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 75 | 22 | 12 | 11 | 9 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | 1 | Introduction of Project and Set up Spring Boot project with MySQL backend | 2026-02-04 | 2026-02-05 | Khushi Rokade | Design | 3- Completed | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 2 | Configure DB connection and Transaction genaration | 2026-02-06 | 2026-02-07 | Khushi Rokade | Integration Test | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 3 | Implementing Fraud Ditection Rule | 2026-02-10 | 2026-02-13 | Khushi Rokade | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 4 | Accept Transaction & Detect Fraud Score via REST API | 2026-02-17 | 2026-02-19 | Khushi Rokade | Others | 3- Completed | 6 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 5 | Implementing ML | 2026-02-20 | 2026-02-26 | Khushi Rokade | Build | 3- Completed | 12 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 6 | Combine ML model With Fraud RullesCompletion | 2026-02-27 | 2026-03-06 | Khushi Rokade | Coding | 3- Completed | 7 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 7 | Simple UI Implementationfuncanality | 2026-03-07 | 2026-03-13 | Khushi Rokade | Integration Test | 3- Completed | 10 | 3 | 0 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 8 | UI improvement and adding more funcanalityRules | 2026-03-15 | 2026-03-20 | Khushi Rokade | Design | 3- Completed | 12 | 3 | 3 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 9 | Fraud Notification in Dashboard And Email notification | 2026-03-23 | 2026-03-26 | Khushi Rokade | Unit Test | 2- In Progress | 12 | 4 | 3 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-001 | 10 | Project Discussion Module 4(Testing and Deployment) | 2026-03-27 | 2026-03-30 | Khushi Rokade | Integration Test | 2- In Progress | 8 | Day 1: 3; Day 2: 0; Day 3: 1; Day 4: 1; Day 5: 1; Day 6: 1; Day 7: 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 2 | Lack of clarity on project requirements | Conducted a detailed discussion with mentors and team
Sprint 1 | Day 4 | Lack of clarity on specific project goals and workflow steps. | Conducted a team brainstorming session and reviewed the project requirements.
Sprint 2 | Day 6 | Agile template confusion | Conducted a meeting where all doubts were clarified by the mentor.
Sprint 2 | Day 7 | Difficulty in identifying all the fraud rules | Conducted additional research and consulted online resources to fill gaps.
Sprint 3 | Day 9 | Difficulty in finding Dataset | Searched on Kaggle and got the exact Dataset
Sprint 3 | Day 12 | Difficulty in intregrating ML model | Discussed with mentor and cleared the dought
Sprint 4 | Day 16 | Confussion in UI implementation | Optimized UI designe with mentor support
Sprint 5 | Day 23 | Project Improvement | Scheduled project review

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2026-04-02 | 2026-06-02 | G Bhagya Sri Lakshmi | Reviewing documentation regularly | Assuming project requirements are clear | Participating in discussions and meetings | Scheduled a review session with team and mentors to clarify project goals
2 | Sprint 2 | 2026-10-02 | 13/2/2026 | Om | Test fraud scenarios properly | Avoid incomplete testing | Follow modular design | Tested all fraud cases
3 | Sprint 3 | 15/2/2026 | 20/2/2026 | Asma Farzana | Optimize rule engine | Avoid complex logic | Use simple conditions | Improved rule performance
4 | Sprint 4 | 24/2/2026 | 28/2/2026 | Pelluru Yujesh Shyam | Improve alert handling | Avoid duplicate alerts | Maintain clean DB structure | Implemented alert filtering
5 | Sprint 5 | 2026-02-02 | 2026-06-03 | Khushi Rokade | Improve ML accuracy | Avoid overfitting | Use proper dataset | Retrained model with better data